# koos-ai Rollout Plan — from proven concept to working capability

Bazooka Labs for Koos · July 2026 · The full plan behind the one-page summary: costs, data handling, risks, and what we need from you.

## 1. Where we stand

The June proof-of-concept did its job. What's ready today:

| Asset | Status |
| --- | --- |
| koos-ai repo — the canon (the single Koos-owned source of truth for tools and knowledge) and the plugin marketplace (the mechanism Claude Code uses to install and update from it), in one | Built, private on GitHub (v0.3.1) |
| Three priority tools as agreed: Contract Checker, Survey Builder, Design Token Generator | Complete — including the companion rule files (survey quality rules, survey structure guide, token naming standards), unchanged from the Build Week originals |
| Knowledge base | Real Koos content: company profile, brand voice; plus a core guardrails draft (Koos review pending — see §4, Phase 0) |
| Feedback loop | Live in the repo, seeded with RJ's real Build Week feedback — including two open actions for Koos legal (§7) |
| Operational guides | Four docs shipped in the repo: setup, designer onboarding, steward guide, how-updates-work |
| Install + update mechanics | Install, the tools (/koos:contract-checker), and the release→update loop all tested end-to-end, desktop app included. One piece left to confirm on your machines in Week 1: automatic pickup at startup (the manual fallback takes 30 seconds) |
| Demo environment | Synthetic "Stadslijn" client project folder incl. a test contract with planted issues — used in the June demo, reusable for onboarding |

What is deliberately not in scope yet: the other Build Week tools (promoted later, one by one), integrations (HubSpot, Google Slides), the lead-gen and search-visibility workstreams (§10).

## 2. One pilot, two tracks, on live work

We start narrow and real. Two tracks, because the tools serve two different workflows:

Track A — Contracts. The Contract Checker runs where contracts actually live: new business (RJ built it for exactly that). Every incoming contract goes through it during the pilot. Anything the tool drafts goes out only after the commercial owner signs off — and legal, where your normal process requires it. Naming that reviewer is part of Phase 0.

Track B — Design & research tools. 2–3 designers use the Survey Builder and/or the Design Token Generator on live project work, as their projects actually need them. This tests the "shared toolkit for designers" story: install, use in a real project folder, feedback, updates.

Everything runs the production way from day one: installed plugin, real project folders, feedback loop, versioned updates. Build Week proved the tools are worth having; the pilot proves the shared way of running them.

## 3. Roles — and what they cost internally

| Role | Who | Time | Responsibility |
| --- | --- | --- | --- |
| Sponsor | Koos (e.g. Saskia/RJ) | ~1 h/wk | Decisions, unblocking, pilot selection, judging the success criteria |
| Steward (recommend naming two) | Koos — git-comfortable | 2–4 h/wk each in pilot | Owns the canon: releases, feedback triage, promotion, anonymisation gate. Full role description: docs/steward-guide.md in the repo |
| Track A owner | Koos — new business (e.g. RJ) | within existing contract work | Runs live contracts through the checker; reviews anything tool-drafted before it goes out |
| Pilot designers | Koos, 2–3 people | their normal work + ~1–2 h total each | Use the tools on real work; log feedback (2 sentences in Slack) |
| Bazooka | Steven | per phase, see §6 | Setup, coaching the steward, tool fixes, pilot support, review |

Internal time, added up: two stewards at 2–4 h/wk over Phase 0 plus the pilot (~4 weeks elapsed) is 16–32 h; sponsor ~4 h; designers ~3–6 h combined. Roughly 25–40 internal hours total — that's the real internal cost to put next to the external one (§6).

Making the steward role stick — this is the choice that matters most in this plan: give it an internal booking code, a place in the review cycle, and a 6-month re-decision point. The profile: a Build Week standout, pragmatic, respected enough that "not yet" sticks. Target after Phase 2: ≤2 h/wk.

## 4. Phased plan

### Phase 0 — Foundation (the week after you confirm the §11 items; ~half a day of sessions)

- You create (or name) a Koos GitHub organisation; we set up the private koos-ai repo there; the interim Bazooka-hosted copy retires.

- You name the steward(s), the Track A owner, and the pilot designers; everyone gets repo access; the #koos-ai Slack channel is created.

- Data & compliance gate — the four checks in §5, resolved before any live client document goes through a tool.

- Guardrails working session (60–90 min, Bazooka + Koos research/practice leads). The current core-guardrails file is a Bazooka draft. This is not a sign-off meeting: your research-ethics and anonymisation practice gets worked in, and your edits become v1. (The full framework is ask #4 in §8.)

- Steward setup session (~2 h): walk the repo, do the steward's first release together (a real small fix), verify install + GitHub auth on their machine.

Exit condition: the steward has shipped a version bump that another machine received via update — and the data gate is green.

### Phase 1 — Pilot (3 working weeks)

Week 1 — Onboard. Bazooka + steward onboard the pilot group (~45 min each: the 15-minute guide, then a ~30-minute session — install, update checks, and a supervised sample run). Baselines are captured before first tool use (Track A: time spent on the last few contract reviews, per the owner). First live contract goes through the checker this week.

Week 2 — Use. Both tracks run on real work. Feedback flows to #koos-ai. The steward runs the weekly triage-fix-release rhythm; at least one release ships mid-pilot, proving the update loop on your machines.

Week 3 — Verify & decide. Steward + Bazooka compile the evidence: usage (from the feedback log and self-reports), time-vs-baseline, feedback→fix cycle times, the Drive-folder verdict, auth/update reliability. Pilot review session: the sponsor judges the criteria (§12) and decides — expand, adjust, or stop.

(Calendar note: three working weeks — with summer holidays, let the elapsed time stretch rather than pilot with half the group away.)

### Phase 2 — Expand (after the pilot review)

- Onboard the next wave with the same guides (repeatable without Bazooka in the room); pick the scale-out mechanism — onboarding script, shared project settings, or settings IT deploys centrally to every Mac ("managed settings") — options in docs/setup-guide.md, Step 5.

- Brief the wider team before this phase — what the toolkit is, what usage data exists (aggregated only; see §5).

- Promote the next tools from the Build Week set, one release at a time. Candidates by evidence and readiness: transcript-analyser, figma-token-checker (its rules file already exists), email-proposal, case-builder. Integration-dependent tools (pitch-builder/Google Slides, am-assistant/HubSpot) only after their integrations are decided.

- Add sector guardrail modules (healthcare first, given VGZ/Santeon-type work), loaded per client sector.

### Phase 3 — Steady state

Steward rhythm on a fixed weekly slot; quarterly tool review (usage, staleness, retirement). Bazooka steps back to a support role. Any further build work (new tools, integrations, the parked workstreams in §10) happens as separately scoped, capped sprints that you trigger.

## 5. Data & compliance — the Phase-0 gate

Plainly: running a tool sends the files you're working on to Anthropic's Claude API — that's how Claude Code works. Installing uploads nothing, and nothing enters the shared repo un-anonymised. But "we put your contract through an AI" is a sentence you need to be able to finish confidently when a VGZ or Rijkswaterstaat asks. Four checks before any live client document goes through:

- Account setup. The pilot runs on your own Claude workspace under Anthropic's commercial terms (business data not used for training; admin control) — not on personal accounts. Decide tier and seats; budget note in §6.

- DPA & processing. Review Anthropic's data-processing addendum (it's part of the commercial terms); confirm retention settings and processing location as part of that review. (We prepare the summary; your legal confirms.)

- Client permission check. A legal sweep of the pilot clients' MSAs/NDAs for AI/subprocessor clauses before their documents go through a tool. Where a contract doesn't permit it: that client's documents stay out of the pilot (or go through in redacted form).

- The client-facing answer, drafted for legal review, so every Koos person says the same thing when asked. Working draft: "We use Claude (Anthropic) as a drafting assistant under a commercial agreement — client data is not used for model training and is handled per our data-processing agreement. A Koos professional reviews everything before it reaches you, and on request we exclude your project from AI-assisted work." [To be reviewed and owned by Koos legal.]

The employee side. Pilot numbers are self-reported totals — no per-person dashboards, nothing measured on anyone's machine — and joining the pilot is voluntary. Before going agency-wide, tell the wider team what the toolkit is and what usage data exists.

## 6. Costs — external, internal, and what stopping costs

|  | Effort | Cost |
| --- | --- | --- |
| Bazooka, Phase 0 — repo handover, data-gate prep, guardrails session, steward setup | [est. 10–14 h] | [rate × hours — per engagement note] |
| Bazooka, Phase 1 — onboarding, weekly support, fixes-as-releases, audit + review session | [est. 16–22 h] | [idem] |
| Koos internal, Phases 0–1 | ~25–40 h (per §3) | opportunity cost, mostly steward |
| Claude licensing | — | Koos's own Anthropic workspace seats for pilot participants (tier decision in the §5 data gate) |

Bracketed effort figures are Bazooka's estimates; rates and totals are in the engagement note that accompanies this plan.

If the Week-3 verdict is "stop": total exposure is the Phase 0–1 hours above, the internal time, and the pilot's Claude seats — and you keep the working toolkit: repo, tools, guides, feedback loop (§9).

## 7. Found along the way: two things for your legal team

Surfaced by the Contract Checker work during Build Week (tracked in the repo's feedback log):

- The Koos T&C still lists Lisbon, Berlin and Oslo as Koos Group offices — current reality is Amsterdam + Abu Dhabi.

- The T&C doesn't make methodology/deliverable use rights conditional on full payment — the Contract Checker flags client contracts for exactly this, so your own paper should match.

Both are small, both predate this project, and fixing them makes tool and contract consistent. Three further researched gaps (participant consent ownership, change-request process, freelancer carve-outs) are logged as candidates for the tool's risk framework.

## 8. Context files: what we have vs. what we need from you

### Already in the canon (real content)

| File | Source | Note |
| --- | --- | --- |
| company.md — who Koos is | Build Week knowledge base | ✔ |
| brand-voice.md — how Koos writes | Build Week knowledge base | ✔ |
| Koos contract baseline (liability, IP/CC-BY-SA, payment ladder, jurisdiction, GDPR…) | Embedded in Contract Checker, from RJ's tool | ✔ — two legal updates pending (§7) |
| survey-quality-rules.md, survey-structure-guide.md | Noor & Ruben's originals | ✔ bundled, unchanged |
| rules.md — token naming conventions & standards | Jasper & Carmel's original | ✔ bundled, unchanged |
| guardrails/core.md | Bazooka draft | ⚠ explicitly labeled "Koos review pending" until the Phase-0 working session |

### Needed from you (the ask list)

| # | What | Feeds | Owner at Koos | When |
| --- | --- | --- | --- | --- |
| 1 | Phase-0 confirmations — GitHub org, steward(s), Track A owner, pilot designers + project, Slack channel | Everything | Sponsor | Phase 0 |
| 2 | Data gate inputs — workspace/tier decision, DPA review, pilot-client contract sweep, sign-off on the client answer | §5 | Sponsor + legal | Phase 0 |
| 3 | Guardrails working session — Koos's research-ethics and anonymisation practice, worked into the core guardrails | Every tool run | Research leads | Phase 0 |
| 4 | The real research-ethics framework as a document (known gap since Build Week) | Knowledge base | Research leads | Phase 1 |
| 5 | T&C updates — the two legal actions in §7 | Contract Checker accuracy | Legal | Phase 1 |
| 6 | Sector sensitivities — existing notes/policies for healthcare, finance, public sector | guardrails/<sector>.md | Practice leads | Phase 2 |
| 7 | Terminology / glossary — the terms Koos insists on (and the misuses it bans) | Consistent tool output | Practice leads | Phase 2 |
| 8 | Services & offering descriptions | Tools that write client-facing text | Sponsor/marketing | Phase 2 |
| 9 | Deliverable formats — the report/proposal structures worth templating | templates/ | Practice leads | Phase 2 |
| 10 | (Per-tool, later) rate card (email-proposal), HubSpot access (am-assistant), Slides template (pitch-builder) | Next promotions | Various | When promoted |

Items 6–9 mostly exist already as decks, wikis and habits — we and the steward turn them into canon files; you review. Nothing gets written from scratch.

## 9. Ownership & exit — in writing

- The repo and everything in it is yours from the Phase-0 handover: tools, guides, guardrails, feedback logs. We recommend stating this explicitly in the engagement terms.

- No key-person dependency by design. Everything is markdown and git. Any steward — or any future vendor — can maintain, extend, or fork it without Bazooka.

- Platform dependency: distribution rides Claude Code's plugin mechanism, which Anthropic may evolve. The content doesn't care — it's portable markdown; worst case, the same tool files keep working as plain Claude Code skills without the marketplace layer while distribution is re-plumbed.

- If the pilot says stop: see §6. The toolkit remains usable as-is for as long as it's useful.

## 10. Explicitly parked (so nothing is silently dropped)

- Lead-generation tooling — parked until the deliverability, GDPR and B-Corp reputation questions are answered (the "multiple sending addresses" idea from June needs a hard look before any build).

- "GEO" (generative-engine optimisation — making Koos show up in AI-generated answers) — separate workstream, unrelated to this rollout.

- Deeper integration layers (an MCP bridge — a technical connection layer between systems — and promotion automation) — trigger-gated: revisit only when manual promotion becomes the bottleneck.

- Remaining Build Week tools — in the team folders, promoted deliberately in Phase 2+.

## 11. What we need confirmed to start (the Phase-0 list)

- GitHub organisation (or green light for Bazooka to create one in Koos's name).

- Steward name(s) — ideally two — plus their booking arrangement (§3) and a slot for the 2-hour setup session.

- Track A owner (contracts) and 2–3 Track B designers, plus the pilot project(s).

- A slot for the 60–90 min guardrails working session with research/practice leads.

- Legal time for the §5 data checks (DPA review + pilot-client contract sweep), and a #koos-ai Slack channel.

## 12. Pilot success criteria — agreed up front, judged by you

Assessed in the Week-3 session by the sponsor. Baselines captured before first tool use.

- Track A: ≥ 3 live contracts through the checker; ≥ 1 tool-drafted amendment sent after the commercial owner's review; time-per-review vs. the pre-pilot baseline, with the target set by the sponsor at kickoff.

- Track B: ≥ 2 real runs of the design/research tools whose outputs were actually used in project work — as judged by the designers.

- The loop lives: ≥ 5 feedback entries from ≥ 2 Koos users (Bazooka's own entries don't count); ≥ 2 releases shipped in response; ≥ 1 release picked up on every pilot machine mid-pilot.

- Operational verdicts, documented: Google Drive workflow (works / workaround / avoid) and update+auth reliability per machine.

- A decision — expand / adjust / stop — made on this evidence.

## 13. Risks & mitigations

| Risk | Status | Mitigation |
| --- | --- | --- |
| Google Drive project folders: Claude Code reading Drive-for-Desktop files has known rough edges (online-only/streamed files; open bug reports) | Partially verified; the pilot settles it | "Make available offline" as standard practice (in the onboarding guide). Plan B if the Week-3 verdict is "avoid": (a) local working folder per project with a defined move-to-Drive step at project close, or (b) Drive stays the archive and active work happens in an offline-marked subset. The call is the sponsor's + steward's, with Week-3 evidence |
| Tools quietly go stale on a machine — background updates on a private repo need a one-time access token per machine, separate from normal GitHub login (documented behaviour; silent when missing) | Known, documented, designed around | Token setup + auth check are hard steps in onboarding; symptom + fix in the troubleshooting table; steward re-checks on any "stale tools" report |
| Auto-update at startup — documented, not yet observed on Koos machines | Doc-confirmed; manual path verified | To be confirmed on the first pilot laptops in Week 1; 30-second manual fallback; the mid-pilot release explicitly rehearses it |
| Steward bottleneck / single point of failure | Structural | Two stewards; booking code + re-decision point (§3); guides make the role transferable |
| Feedback loop goes quiet | The usual failure mode | Two-sentence bar; steward closes the loop visibly (what shipped, who flagged it); explicit success criterion (§12.3) |
| Client data enters the canon | Prevented by design | Only the steward writes to the canon; anonymisation gate on promotion; Build Week folders (which contain real client documents) are never copied wholesale |
| A tool output reaches a client unreviewed | Process | Track A has a named reviewer before anything goes out; designer-in-the-lead is in the guardrails and the onboarding framing |
| Compliance surprise (client contracts) | Addressed up front | The §5 gate runs before live documents; the team briefing precedes scale-out |

## 14. What we deliver per phase

| Phase | Deliverables | Effort |
| --- | --- | --- |
| 0 | Repo handover to the Koos org; data-gate preparation (DPA summary, client-answer draft); guardrails working session; steward setup session; onboarding materials (done — in the repo) | [est. 10–14 h] |
| 1 | Designer + Track A onboarding; weekly support; fixes shipped as releases; pilot audit + review session | [est. 16–22 h] |
| 2 | Next-tool promotions (per tool: harden, package, release); sector guardrail modules with practice leads; scale-out mechanism | scoped after the pilot decision |
| 3 | Support + separately scoped, capped build sprints on Koos's trigger | per sprint |

## Appendix — claim verification status

Because this plan makes operational promises, here's what's tested and what isn't. Verified by doing (multiple machines, June–July 2026): the install commands; the desktop-app GUI path with a private repo; namespaced skill invocation; the full release→marketplace-refresh→plugin-update loop; the settings blocks Claude Code writes on install; the bundled rule files byte-identical to the Build Week originals. Documented, pilot-verifies: automatic update pickup at startup on designer machines; team pre-provisioning (Claude Code prompting to add the marketplace when a shared project declares it). Known behaviours and issues, designed around (documented by Anthropic or on the public Claude Code issue tracker): marketplace remove/re-add doesn't refresh; enabledPlugins doesn't auto-install; background updates on private repos need an environment token (missing token fails silently); Google Drive online-only files. Details and sources live in the repo's docs/.